## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | NA | Sparsh Modi | 3- Completed
S1 | S1 | US-001 | Project basic environment install & setup | MUST HAVE | NA | Sparsh Modi | 3- Completed
S2 | S2 | US-001 | Learned tools & worked on data creation, insertion , multiprocessing and pattern matching | SHOULD HAVE | NA | Sparsh Modi | 3- Completed
S2 | S2 | US-001 | Implemented rule engine, connected database with chunk results, improved project structure and added README explanation. | SHOULD HAVE | NA | Sparsh Modi | 3- Completed
S3 | S3 | US-001 | Added Dynamic Chunking, Sentiment Analysis, Execution Time & Replace .txt with .csv file. | SHOULD HAVE | NA | Sparsh Modi | 3- Completed
S4 | S4 | US-001 | Built Streamlit dashboard with Upload & Process tab, real-time progress bar, and SQLite integration | MUST HAVE | Streamlit, SQLite | Sparsh Modi | 3- Completed
S5 | S5 | US-001 | Added multi-format file support (CSV, Excel, JSON, TXT), Overview, Search & Filter, Analytics tabs | SHOULD HAVE | Pandas, Plotly | Sparsh Modi | 3- Completed
S6 | S6 | US-001 | Completed Live Analyzer, Export tab, colorized table, keyword search, and final README documentation | SHOULD HAVE | openpyxl, Streamlit | Sparsh Modi | 3- Completed
Note on F1: ====== ID#AAAB0gF_ue8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 82 | 28 | 25 | 14 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project | 2026-02-09 | 2026-02-10 | Sparsh Modi | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Project basic environment install & setup | 2026-02-11 | 2026-02-12 | Sparsh Modi | Others | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Learned tools & worked on data creation, insertion , multiprocessing and pattern matching | 2026-02-13 | 2026-02-18 | Sparsh Modi | Coding | 3- Completed | 8 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Implemented rule engine, connected database with chunk results, improved project structure and added README explanation. | 2026-02-19 | 2026-02-24 | Sparsh Modi | Build | 3- Completed | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Added Dynamic Chunking, Sentiment Analysis, Execution Time & Replace .txt with .csv file. | 2026-02-25 | 2026-03-02 | Sparsh Modi | Coding | 3- Completed | 12 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-001 | 1900-01-05 | Implemented Multiprocessing Pool (5 workers) for parallel chunk processing | 1900-01-04 | 2026-03-05 | Sparsh Modi | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-06 | Added SQLite database integration with duplicate-skip logic | 2026-03-06 | 2026-03-08 | Sparsh Modi | Build | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-07 | Regex-based keyword detection and 50+ word sentiment dictionary | 2026-03-09 | 2026-03-11 | Sparsh Modi | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-08 | Negation handling (3-word window) and intensity multiplier logic | 2026-03-12 | 2026-03-14 | Sparsh Modi | Coding | 3- Completed | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-001 | 1900-01-09 | Built Streamlit Upload & Process tab with file conversion and live progress bar | 2026-03-15 | 2026-03-17 | Sparsh Modi | Build | 3- Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-10 | Implemented Overview tab: KPI metrics, donut chart, trend line, exec time chart | 2026-03-18 | 2026-03-20 | Sparsh Modi | Design | 3- Completed | 8 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-11 | Built Search & Filter tab with colorized table, sliders, and keyword search | 2026-03-21 | 2026-03-23 | Sparsh Modi | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-12 | Added Analytics, Live Analyzer and Export tabs with download options | 2026-03-24 | 2026-03-25 | Sparsh Modi | Build | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAAB0hMbhTg Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB0hMbhUA Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAB0hMbhTo Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAB0gF_ue4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAB0hMbhTc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB0hMbhTE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAB0hMbhTI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB0hMbhTM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB0hMbhTw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB0hMbhT8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB0hMbhTU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB0hMbhTs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB0hMbhTY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB0hMbhT4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB0hMbhT0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB0hMbhTQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB0hMbhTk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Unclear understanding of parallel text processor project scope and objectives. | Conducted a detailed kickoff discussion with mentor to align on project goals.
Sprint 1 | Day 3 | Difficulty setting up Python virtual environment and installing all dependencies. | Resolved setup issues by following official docs and consulting team members.
Sprint 2 | Day 5 | Confusion about multiprocessing Pool usage and chunk pipeline architecture. | Reviewed Python multiprocessing documentation and ran small test scripts.
Sprint 2 | Day 7 | Regex keyword detection returning incorrect results due to missing word boundaries. | Debugged regex patterns using Python shell and fixed \b word boundary expressions.
Sprint 2 | Day 9 | Negation and intensifier logic in sentiment engine not working as expected. | Redesigned window-based negation check and validated on sample IMDb reviews.
Sprint 3 | Day 11 | Streamlit file uploader not correctly parsing Excel and JSON multi-format files. | Added explicit format detection and silent conversion logic in file_to_reviews().
Sprint 3 | Day 13 | Plotly charts had rendering inconsistencies with light theme styling. | Standardized paper_bgcolor to white and adjusted all color variables in theme dict.
Sprint 3 | Day 14 | CSV export produced encoding issues when opened in Excel. | Changed export encoding to utf-8-sig to ensure full Excel compatibility.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-11-04 | 2024-11-06 | Sparsh Modi | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2 | Sprint 3 | 2024-11-16 | 2024-11-22 | Sparsh Modi | Prioritizing Python practice | Delaying review of tasks | Maintaining focus on coding | Achieved Python kit completion on time
3 | Sprint 4 | 2024-11-23 | 2024-11-29 | Sparsh Modi | Preparing SQL practice | Rushing through SQL concepts. | Asking for help when stuck. | Completed SQL with support from the team
4 | sprint 5 | 2024-12-02 | 2024-12-06 | Sparsh Modi | Participating in Milestones discussions | Delaying voice input exploration | Collaborating on language processing strategies | Completed voice input prototypes and received team feedback for improvements.